## 📊 SUMMARY
INTELLEGO · ACTION ITEMS DASHBOARD
Week of 17 April 2026
TOTAL ACTIVE ITEMS | DONE / COMPLETED | IN PROGRESS (WIP) | PENDING | ONGOING
32 | 7 | 11 | 20 | 1

## 📋 CLIENT ACTION ITEMS
CLIENT ACTION ITEMS · As at 17 April 2026
CLIENT | ACTION ITEM | STATUS | OWNER (CRM) | DATE RECEIVED | TARGET DATE | UPDATE (PREV WEEK) | UPDATE (THIS WEEK)
CLIENT NAME | ACTION ITEM | STATUS QUO | CRM | DATE RECEIVED | TARGET COMPLETION DATE | UPDATE PREVIOUS WEEK | UPDATE THIS WEEK
Shamva | IPS and mandates request | WIP | Tatenda | 2026-01-01 | 2026-03-16 | Data for the IPS was requested from the Administrators, Mandates will be finalised after the IPS review | Data for the IPS was requested from the Administrators, Mandates will be finalised after the IPS review
Nestle | IPS Review | WIP | Tari | 2026-02-19 | 2026-03-31 | Data was requested from the administrator however we are waiting for the actturial report to be finalised | Data was received from the administrator excluding replacement ratios
First Capital Bank | Medical Investments Disinvestment Paper | WIP | Tari | 2026-02-24 | 2026-03-13 | Welcome is to communicate with the CEO of Cimas to see whether they are still buying shares on the medical investment. | Welcome is to communicate with the CEO of Cimas to see whether they are still buying shares on the medical investment.
Zimplow | Assesment on suitability of property invesrment opportunity | DONE | Tatenda | 2026-02-13 | 2026-03-20 | There was request for further information on the Investment opportunity, yet to receive a response from minerva | Assesment on suitability of property invesrment opportunity was done.
Masiyepambili | The board requested that we include long term asset manager perfomance survey numbers in future reports | On going | Edwin | 2026-03-10 | On going | This is to be included in the next client report | Nothing has been done yet on this action item. To be actioned in the next client report
| Ruzawe project analysis | Pending | Edwin | 2026-03-10 | 2026-03-31 | Requested the information and necessary data from the asset manager without a response | Requested the information and necessary data from the asset manager without a response
| NBS proposal recommendation and analysis | Pending | Edwin | 2026-04-24 | 2026-05-11 | Draft in place pending review | Draft was circulated for review by team members.
| 3 year fund perfomance analysis | WIP | Edwin | 2026-03-10 | 2026-03-31 | Cross checking 2023 performance numbers with the report sent to Client. | Performance Analysis done, to circulate for team members review
Whitestone | Zimcampus project returns from inception to date | Pending | Edwin | 2026-03-11 | 2026-03-31 | Still compiling data | Still compiling data
| Three year perfomance analysis of the Smartvest portfolio | WIP | Edwin | 2026-03-11 | 2026-03-31 | Cross checking 2023 performance numbers with the report sent to Client. | Performance Analysis done, to circulate for team members review
| Available investment from Nhaka Disposal and funds that may come from the Smartsurbubs disposal. | Pending | Edwin | 2026-03-11 | 2026-03-31 | Draft was circulated for review | To circulate amended draft to team members
NSSA | Glenforest Opportunity Recommendation | Pending | Tari | 2026-03-11 | 2026-04-10 | The asset is not yet investor ready given that the funds required are mostly dependent on the finalisation of the the Brick and Mortar Project. | Requested contractor profiles and other necessary information for an analysis,However the project is not yet ready and is highly dependent on the brick and Mortar Project
| Mortgage pass though fund-Recommendation | Pending | Tari | 2026-03-11 | 2026-04-10 | Nothing has been done yet on this action item | Nothing has been done yet on this action item
Zimasco | Update on report on the Fund’s liquidity profile assessment and review of investment strategy | Pending | Tapiwa | 2026-03-09 | 2026-03-31 | This is to be addressed in the Fund's Strategy Session that is to be scheduled by the Administrator | This is to be addressed in the Fund's Strategy Session that is to be scheduled by the Administrator
| Asset prevailing market values in MBIZO area where the Fund holds stands | Pending | Tapiwa | 2026-03-09 | 2026-03-31 | This is to be addressed in the Fund's Strategy Session that is to be scheduled by the Administrator | This is to be addressed in the Fund's Strategy Session that is to be scheduled by the Administrator
| Review and issue recommendations on Fairview stand offer submitted by Datvest. | Pending | Tapiwa | 2026-03-09 | 2026-03-31 | This is to be addressed in the Fund's Strategy Session that is to be scheduled by the Administrator | This is to be addressed in the Fund's Strategy Session that is to be scheduled by the Administrator
| 5 Year Asset manager Perfomances | Pending | Tapiwa | 2026-03-16 | 2026-04-30 | Nothing has been done yet on this action item | Nothing has been done yet on this action item
Bright | Recommendation on PA and Offshore Investments | Pending | Tapiwa | 2026-03-26 | 2026-04-10 | Nothing has been done yet on this action item | Nothing has been done yet on this action item
FCB | IPS Review | Pending | Tari | 2026-03-27 | 2026-04-30 | Data has been requested | Received Data excluding replacement ratios
MIWF | OMIG Agreement Draft | DONE | Edwin | 2026-01-01 | 2026-03-30 | Draft was circulated for review | OMIG Agreement sent to client
The Joseph | Ruzawe project analysis | WIP | Tapiwa | 2026-04-04 | 2026-04-30 | Nothing has been done yet on this action item | The data required for the analysis was requested without a response yet
Econet | IPS Review | Pending | Tari | 2026-04-09 | 2026-04-30 |  | Requested for the data required for this action item , yet to get a response from the administrator
| Analysis comparing the merits of the Bambanani renovations versus disposing of the property | Pending | IREA | 2026-04-09 | 2026-04-30 | Requested the information and necessary data from the administrator without a response | The data was received and the request is being actioned by IREA
ZAPF | IPS Formulation | WIP | Elvis | 2026-03-28 | 2026-04-30 | This was circulated for review yet to get feedback | This was circulated for review yet to get feedback
ABC | Mortgage pass though fund | Pending | Tapiwa | 2026-04-16 | 2026-04-30 |  | The Fund has requested an Adhoc meeting with the asset manager first , before issuing our recommendation
CIPF | Eagle Mortgage Pass Through | WIP | Tatenda |  | 2026-05-14 | Draft is currently under review | Still inputing review feedback
| Dominium Global Fund | WIP | Tatenda | 2026-03-11 | 2026-05-14 | Due dilligence still underway | Waiting for asset manager to share the due dilligence questionnier by thr 17th of April.
| IPS Review | WIP | Tatenda | 2026-03-15 | 2026-05-30 |  | Requested data only received Fund Rules
| Sanlam Recommendation | DONE | Tatenda | 2026-04-14 | 2026-05-14 | Requested for updated perfomance reports on the asset , yet to receive this informantion | Sanlam Recommendation Done
CAAZ | Centrawest Recommendation | Pending | Tari | 2026-04-29 | 2026-05-03
Mimosa | Deep Dive Mangwana Perfomance Since Inception | Pending | Tari | 2026-05-06 | 2026-06-01
NSSA | Asset manager perfomance assesment in comparison to objectives set in the previous strategy | Pending | Tari | 2026-05-09 | 2026-06-30

## ✅ COMPLETED ITEMS
COMPLETED ACTION ITEMS · Historical Record
CLIENT | ACTION ITEM | STATUS | OWNER (CRM) | COMPLETION DATE
ABC | Tigere Recommendation | Done | Tarie | 2023-04-30
Anglo American PF | Consultancy Proposal | Done | Vongai | 2023-04-30
BOC | Recommendation for Smart suburbs, there is an ongoing capital call | Done | Farai | 2023-04-30
BOC | Update Report Request | Done | Farai | 2023-04-30
BOC | Mandara Cluster Recommendation | Done | Farai | 2023-04-30
Brands | Tigere recommendation | Done | Tarie | 2023-04-30
BRANDS | TIGERE VIA SMATVEST | Done | TARIE | 2023-04-30
CAAZ | Foundry Project Reccomendation | Done | Tariei | 2023-04-30
CIPF | USD alternative investments | Done | Vongai | 2023-04-30
CIPF | Agrowth Recommendation – an increase in exposure | Done | Vongai | 2023-04-30
CIPF | construction bonds analysis | Done | Vongai | 2023-04-30
CIPF | ACL Leasing Bonds investment analysis | Done | Tapiwa, Farai | 2023-04-30
CIPF | Agrowth Recommendation | Done | Vongai, Tapiwa | 2023-04-30
CIPF | Investments Report | Done | Tino, Vongai | 2023-04-30
CIPF | USD Recommendations | Done | Tapiwa, Tapiwa | 2023-04-30
CIPF | LIST OF USD ASSETS- standard template created for other clients | Done | Tapiwa | 2023-04-30
Dairiboard | Recommendation for warehouse construction, foundry, solar project | Done | Shandurai, Farai | 2023-04-30
Dairiboard | Supervisory Agreement/ Consultancy Agreement | Done | Farai/Shandu | 2023-04-30
Dairiboard | Need to verify numbers for Mandara cluster houses in order to confirm Dairboard additional contributions | Done | Shandu/ Farai | 2023-04-30
Dairiboard | Clarify investment terms from initial recommendation and supporting documents. | Done | Shandu/ Farai | 2023-04-30
Dairiboard | Gold Coins | Done | Farai | 2023-04-30
Dairiboard | To follow up with the nhaka team on nurture status update | Done | Farai | 2023-04-30
Dairiboard | Update Report Request | Done | Farai | 2023-04-30
Econet | Short paper on target portfolio structure vs current so as to highlight areas of correction as per IPS | Done | Tarie | 2023-04-30
Econet | Recommendation for Mangwana rights issue | Done | Tarie | 2023-04-30
Econet | Check composition of guaranteed fund, bonus history and postulate if they are likely to declare a bonus this year. You can also check with the FML guys. | Done | Tarie | 2023-04-30
Econet | To evaluate the offer for their Vic Falls property which I circulated weeks back and do a recommendation | Done | Tapiwa | 2023-04-30
Econet | To Review the property valuation guidelines from SECZ and propose modifications which we can provide as guidance to clients holding properties especially in light of changing economic environment | Done | Kuda | 2023-04-30
Econet | Paper on VFEX performance- since inception. Zero in on last quarter (graphs, stats, etc will help). Also then talk about why companies are migrating there and possible implications. | Done | Lazarus | 2023-04-30
Econet | Origen Recommendation – | Done | Tapiwa, Tarie | 2023-04-30
Econet | Comparison of Agrowth, Origen and the Agrobills | Done | Tapiwa, Tarie | 2023-04-30
Econet PF | 4Q22 Executive Summary | Done | Shandu, Tarie | 2023-04-30
Engen | Agrowth recommendation | Done | Tapiwa | 2023-04-30
FBC | Concerns over their PA status | Done | Farai, Shandu, Tarie | 2023-04-30
FBC | To send an updated status inclusive of Tigere – PA status likely to go up to 22% | Done | Farai, Shandu, Tarie | 2023-04-30
FBC | FBC Bank Compliance Status | Done | Farai | 2023-04-30
Freda Rebecca | Recommendation on USD opportunities for consideration by the Trustees (Agrowth, Origen etc). | Done | Vongai, Farai, Shandu | 2023-04-30
Freda Rebecca | To provide Trustees with more information on the TDB Offshore opportunity for consideration. | Done | Vongai, Farai, Shandu | 2023-04-30
Freda Rebecca | Resolution to be passed on Tigere Debenture and North West additional Capital Injection | Done | Vongai, Shandu | 2023-04-30
Freda Rebecca | To do due diligence on Mandara Clusters (Smartvest), To create a template and provide a recommendation for the Trustees | Done | Farai | 2023-04-30
innscor | Mopani Recommendation | Done | Shandu | 2023-04-30
Innscor | October Update | Done | Shandu/Vongai | 2023-04-30
IPF | Intellego to Update the committee on guidelines for investing in collective investment schemes | Done | Tarie, Welcome | 2023-04-30
Mcaz | Recommendation for Zimcampus. They want to follow up on their rights | Done | Tapiwa | 2023-04-30
Mimosa | Invictus share Linked Note Recommendation | Done | Vongai, | 2023-04-30
MIMOSA | IPS INPUT FROM CORONATION RISK ADVISORS- Intellego team to meetup with coronation working group to discuss tasks allocated to the team | Done | Vongai, Farai, Welcome | 2023-04-30
NOIC | Recommendation on Mangwana rights issue and other suitable USD investments | Done | Tarie | 2023-04-30
NOIC | Update Report Request | Done | Tarie | 2023-04-30
NSSA | Mangwana Rights Issue | Done | Tapiwa/ Shandu/Tarie | 2023-04-30
Petrotrade | Recommendations on USD investments | Done | Farai, Tino | 2023-04-30
PSMAS | PF Compliance Roadmap | Done | Shandu, Vongai | 2023-04-30
Public Services Pension Fund | Expression of Interest | Done | Vongai | 2023-04-30
Saint Gobain | Tigere Recommendation | Done | Tapiwa, Shandu | 2023-04-30
SCBZ | Recommendation to include all alternative investments in the market which you believe are attractive for the Fund | Done | Tapiwa, Shandu | 2023-04-30
St Johns | Considering investing in Nhaka, Tigere and also reducing their exposure to listed equities/ | Done | Tarie, Shandu | 2023-04-30
Stanbic | Concerns arose around their low PA status and the actions they should take in order to boost it. | Done | Farai, Tarie | 2023-04-30
Stanbic | The fund agreed to invest in Agrowth and TDB, two assets that both have PA status | Done | Farai, Tarie | 2023-04-30
The Avenues Clinic | Consultancy Proposal | Done | Vongai, Welcome | 2023-04-30
The Joseph PF | Usd investment - requested a recommendation for Sanlam Umbrella Fund and we are currently waiting on information from Zimnat, they said they will send mid next week. | Done | Farai, Shandu | 2023-04-30
The Joseph PF | Zimnat Sanlam Wealth Offshore Investment Opportunity Analysis | Done | Tapiwa, Farai | 2023-04-30
The Joseph PF | USD Investment recommendation | Done | Farai | 2023-04-30
The Joseph PF | An analysis of Nhaka focusing on whether they could increase their shareholding | Done | Farai, Shandu | 2023-04-30
TIMB | TDB, Agrowth, Mangwana and TSL Warehouse Recommendation | Done | Vongai | 2023-04-30
TIMB | Engage Invesci to do two valuations for the warehouse investment – in ZWL and USD | Done | Vongai | 2023-04-30
TIMB | Provide Auditors valuation of Mangwana after its approved by its Board (31 March 2023) | Done | Vongai | 2023-04-30
TMP | IPS | Done | Shandu | 2023-04-30
Tongatt | To confirm cash balances and contributions. | Done | Tarie | 2023-04-30
Tourism Industry PF | Consultancy Proposal | Done | Vongai, Welcome | 2023-04-30
TRB | Mangwana Rights Issue Recommendation | Done | Tarie | 2023-04-30
TRB | Mangwana USD Recommendation | Done | Tarie | 2023-04-30
Zimasco | Heka Bond Recommendation | Done | Vongai | 2023-04-30
Zimasco | Mangwana Recommendation | Done | Vongai | 2023-04-30
Zimnat Life | Consultancy Agreement | Done | Vongai, Chris | 2023-04-30
Zimnat Life | Consultancy Proposal | Done | Vongai | 2023-04-30
Zimplow | Gold Coins Recommendations | Done | Tarie | 2023-04-30
Zimplow | Update Report Request | Done | Tarie | 2023-04-30
ABC | Identify alternative investment opportunities for the Fund to deploy ZWL into USD generating assets | Done | Vongai | 2023-06-02
CIPF | IPS Review | Done | Vongai | 2023-04-30
IDBZ | 31 March Update | Done | Vongai | 2023-04-30
ABC | To indicate the value of the portfolio at other rates (scenario analysis) in the report and update | Done | Vongai | 2023-06-02
Zimnat staff PF | Consultancy Agreement | Done | Vongai | 2023-04-30
SCBZ | Review the Asset Split proposal and revert with any feedback by 31 May 2023. Also liase with administrator and asset management on cashflow management modalities under the two sub-accs given that pensioners were largely paid from new contributions (sub-acc 1) whilst their assets are largely in sub-acc 1. | Done | Vongai | 2023-06-20
SCBZ | OMP to be requested to do their valuation reports in both ZWL and USD | Done | Vongai | 2023-06-20
SCBZ | Intellego reports to show stress tests of full financial position of the Fund | Done | Vongai | 2024-06-20
ABC | To intensify efforts to go offshore-to URGENTLY submit overall offshore exposure for the Fund to IPEC in application for investment in TDB (Intellego and OMIG) | Done | Shandu
NOIC | IPS Review | Done | Tarie
Econet | Review Asset Allocation for the conservative group | Done | Tarie
NOIC | Property Recommendation | Done | Tarie
St Johns | Give a recommendation on USD assets (1week) | Done | Tarie
BOC | To send monthly reports in time- team to Prioritise | Done | Farai
BOC | Terms of Reference with Discretionary Limits for Investments Committee to be circulated to members for input before tabling for approval at next Trustees meeting | Done | Farai
Stanbic | Fund requested recommendation on Agrowth as it works on improving PA status. | Done | Farai
SANDVIK | TO COMMUNICATE WITH THE TRUSTEE FOR AN INVESTMENT TRAINING SESSION | Done | Tarie
Zambezi River | PA Complinace ,need for a compliance roadmap | Done | Tapiwa
Engen | Send recommended investments for the USD cash sitting in the account; take up with OMIG on contributions sitting in Nostro (Sub-acc 3 all invested in money market) | Done | Tapiwa
Mcaz | IPS Road map | Done | Tapiwa
Harvest Capital | Due Diligence | Done | Tapiwa
Engen | PPC solar recommendation | Done | Tapiwa
BOC | Recommendation for Leengate housing offer | Done | Tapiwa
Caledonia Mining Services | Green Bond Opportunity | Done | Tapiwa
Mimosa | Mangwana Rights Issue proposal | Done | Vongai
Datlabs | Reconcile the total fund value between CABS and Intellego | Done | Tino
Datlabs | Provide short report on the unlisted shares and unlisted properties held by the Fund | Done | Tino
Datlabs | Nhaka to ensure the certificate is serialized by the end of the month. | Done | Tino
Datlabs | ABCAM to do a write-up and provide more insights into the Tynwald stands to prove the returns generated | Done | Tino
Datlabs | Concerns over extended delays with the finalization of alternative investment projects regarding the Harava Solar Park and Bulawayo Student accommodation projects. The Trustees had concerns of the viability of these projects as well as their liquidity. May you kindly prepare separate assessment reports for these investments updating Trustees on expected timelines for finalization, presenting your views on the viability of these projects going forward and your recommendations based on those views. May you also provide detail on the ease of disposal/liquidity of these investments and provide illustrative scenarios for the expected gain or loss that may arise depending on the timing of disposal for example if investment were to be liquidated immediately versus after completion. May you also provide your recommendation as far as disposal is concerned. | Done | Tino
Datlabs | Unlisted Property and equity investments – Trustees requested a write up on these investments. I believe these are held primarily in the form of Astra shares and the Tynwald property investment both held through ABCAM. May you provide your report touching on the same areas as for the alternative investment assessment report. | Done | Tino
Datlabs | May you kindly reconcile your Prescribed Assets reporting with that of the Custodian so that the correct position may be verified. | Done | Tino
Datlabs | May you also attend to the issue of the revised Asset Manager agreements we discussed and do this for all the Bulawayo Funds | Done | Tino
Edgars | An extended three year USD value trend analysis for the Fund to be shared. In addition, the fund requested recommendations for USD assets in the market. | Done | Tino
Edgars | Assessment of the asset managers’ performance and make recommendations on whether they should continue or fire the asset manager. | Done | Tino
Edgars | They want us to calculate USD performances going forward | Done | Tino
Engen | Engage CABS Custodial to advise them of portfolio under ZB Life | Done | Tapiwa
Engen | Minerva to send Intellego copy of CABSCUS SLA. We need to ensure we have copies of all signed SLAs for custodians | Done | Tapiwa
Engen | Correct the PA level after taking into account ZB compliance level | Done | Tapiwa
Engen | Resolution for investment into the TDB bond to be signed and OMIG to utilise USD36k in Nostro into TDB (to reach the 15% limit). OMIG already started process of deployment and expect to be done by July | Done | Tapiwa
Engen | Do a paper to look at pros and cons of guaranteed fund and advise whether and when to exit | Done | Tapiwa
Engen | Reports to show separate USD and ZWL | Done | Tapiwa
Engen | Do two sets of accounts – one for IPEC and another with hyperinflation accounting – to remove the audit qualification | Done | Tapiwa
Engen | Ensure physical split of assets including bank accounts. Asset managers provided the split but haven’t implemented as yet. | Done | Tapiwa
Falcon | Report separately USD and ZWL assets. We can do this as an appendix as the main reporting currency for sub-Fund 1 and 2 remains ZWL. | Done | Tino
Falcon | Member education to ensure members don’t over-rely on pensions and have own investments e.g. savings into Nhaka retail product. Also look at increasing employer contributions (Minerva). | Done | Tino
Falcon | Nhaka to serialise share certificates and produce every year (client can still verify every quarter) | Done | Tino
Falcon | Datvest to circulate the solar project proposal | Done | Tino
Falcon | Agrowth Recomendation | Done | Tino
IPF | Completion of guidelines on collective investment schemes | Done | Tarie
St Johns | IPS Review | Done | Tarie
NSSA | Update on addendums amendments for the Asset Managers agreements to incorporate the new guidelines by IPEC | Done | Shandu
NSSA | To conduct a performance analysis report on all the Asset Managers based on all factors highlighted in the meeting pack | Done | Shandu
IDBZ | USD Recommendations as client has a usd balance ready for deployment | Done | Shandu
Minerva Funds | Zimgas Investment opportunity | Done | Shandu
Minerva Funds | Nhaka | Done | Shandu
NSSA PF | asset manager fees evaluation | Done | Shandu
Tongatt | Carrick Creagh development funding; pending finalization, initial analysis has been shared with key stakeholders (target date 23/12/22) | Done | Shandu
IDBZ | We were tasked with coming up with the best fixed income instruments of a short term with PA status that the Fund can invest its USD balances in. | Done | Vongai
SCBZ | Track the outstanding rental on Mbano and ensure its included in the reports. Need to lobby with the other institutional shareholder (Tongaat funds) to push for a conversion of the outstanding rentals into equity. Conduct a revaluation of the property once rentals start flowing in. | Done | Vongai
SCBZ | Mount Pleasant Landbank Proposals - Review | Done | Vongai
TIMB | Send recommendations for Mangwana and Nhaka for approval by Trustees via round-robin | Done | Vongai
Astra | Comments on property valuations methods currently being used were requested, team to generate guidelines for property and all alternative investments and set workshop inhouse before circulating to clients and SEC. | Done | Tapiwa
Engen | Engage CABS Custodial to advise them on portfolio under ZB Life | Done | Tapiwa
FBC | A recommendation for Frontier Real Estate Debenture-Intellego | Done | Tapiwa
Saint-Gobain | Historic Performance over a long term period -3years to track Performance of the Fund | Done | Tapiwa
Saint-Gobain | In terms of timeline for the investments- Nhaka Investment then start looking at the 15% foreign offshore investment exposure | Done | Tapiwa
BOC | Nhaka – include option for members to get biological assets. | Done | Farai
Dairibord | TSL Warehouse Investment opportunity | Done | Farai
FBC | A recommendation for Frontier Real Estate Debenture-Intellego | Done | Farai
IDBZ | We were tasked with coming up with the best fixed income instruments of a short term with PA status that the Fund can invest its USD balances in. | Done | Vongai
SCBZ | Track the outstanding rental on Mbano and ensure its included in the reports. Need to lobby with the other institutional shareholder (Tongaat funds) to push for a conversion of the outstanding rentals into equity. Conduct a revaluation of the property once rentals start flowing in. | Done | Vongai
SCBZ | Mount Pleasant Landbank Proposals - Review | Done | Vongai
TIMB | Send recommendations for Mangwana and Nhaka for approval by Trustees via round-robin | Done | Vongai
Hippo | Do a revised Compliance Plan/Roadmap incorporating all new developments and expected cashflow movements and share with the IC. Engagements to be held with IC and Minerva if this can be shared with the regulator as yet. | Done | Shandu
Hippo | Furnish Trustees with more information on Nhaka and get Kevin to present to the members if need be. | Done | Shandu
Minerva | To revise Asset allocation for conservative group | Done | Shandu
Minerva Copvol | Trustees proposing increased exposure to Origen. | Done | Shandu
Seedco | IPS Review | Done | Shandu
TMP | Tidy up reporting to show USD assets and ZWL assets separately | Done | Shandu
TMP | Recalculate the exposure to Delta as at 31 May 2023 after the recent movement in the interbank auction rate and advise the IC Chair for any action if over-exposure remains. | Done | Shandu
IDBZ | Reconcile the Property figures | Done | Vongai
Mimosa | IPS finalisation after incorporating input from Risk Committee | Done | Vongai
SCBZ | There is need to do some deep dive as a committee in terms of carrying out the split in assets so that the end result preserves value on both the Actives and non-actives - Actives moving to the new buyer and the non-actives finding a new home- available options: Unitisation? | Done | Vongai
MMCPF | Risk and Compliance | Done | Vongai
Innscor | Circulate pension fund performance survey comparison | Done | Vongai
St Johns | To help OMIG in seeking clarity on the Copper Meadows property from Atria or property world | Done | Tarie
SCBZ | To consolidated with the two asset managers on the TDB investment so as ensure that the investment does not exceed the 15% threshold | Done | Vongai
Simbisa | Invesci- To Follow up on the valuations, their strategy on Property and usd cash balances | Done | Vongai
Simbisa | Omig- Value on excising the econet rights and meeting will be held on the 8th | Done | Vongai
SCBZ | Intellego to look at the possibility of packaging Goodhope and Mount Pleasant into a REIT | Done | Vongai
ABC | Engage OMIG on how the Fund can participate in Balltech despite their low Fund size | Done | Vongai
EY | IPS | Done | Vongai
Innscor | To receive data on contributions from minerva | Done | Vongai
MIMOSA | Trustees requested for the 1Q23 report to be shared | Done | Vongai
Petrotrade | Evaluate and calculate how much more the Fund can invest through NBS to unlock more mortgage loans for members as there were many still on waiting list and previous limit had been breached. Consider migrating to a USD scheme. | Done | Lazarus
IPF | Report | Done | Tino
Mimosa | Mimosa the investment report for the Fund as at 31 March 2023 for noting by the Committee Members | Done | Vongai
Falcon | Report separately USD and ZWL assets. We can do this as an appendix as the main reporting currency for sub-Fund 1 and 2 remains ZWL. | Done | Tino
Falcon | Member education to ensure members don’t over-rely on pensions and have own investments e.g. savings into Nhaka retail product. Also look at increasing employer contributions (Minerva). | Done | Tino
Falcon | Nhaka to serialise share certificates and produce every year (client can still verify every quarter) | Done | Tino
Falcon | Datvest to circulate the solar project proposal | Done | Tino
Unicem | Separate report for equities between local equities and foreign (including VFEX) equities | Done | Tino
Unicem | Draft PA Compliance Plan for IPEC and also engage Chair and Stephen Nyabadza on applying for PA status for the Grainbags project | Done | Tino
Whitestone | Report separately USD and ZWL assets. We can do this as an appendix as the main reporting currency for sub-Fund 1 and 2 remains ZWL. | Done | Tino
Whitestone | Nhaka investment – make recommendations for the Fund to invest incoming USD contributions into Nhaka. Also consider other assets we can invest USD contributions for investment. Nhaka to be considered for personal retirement planning for members as well (Minerva). Come up with a proposal in liaison with Minerva. Also consider consortiums for segregated herds. | Done | Tino
IPF | Intellego to circulate information on the Eastern and Southern African Trade Fund investment opportunity and (ii) also to relook at your benchmarks | Done | Tino
CIPF | An independent evaluation to go in support of the IC’s recommendation for the Dabuka investment to the Trustees - 15/09/2023 | Done | Vongai
Mimosa | Intellego to share A paper on the Greenfields Recommendation before 15/09/2023 - Target 5% into Greenfields Investment – Rollover the 100k previously invested in the Frontier maturing on the 26th of Sep | Done | Vongai
St Johns | To do a recommendation on the Tigere Debenture once we finalize our due dilligence | Done | Tarie
TRB | GREENFIELDS RECOMMENDATION | Done | Tarie
Zimasco | GREENFIELDS RECOMMENDATION | Done | Vongai
BOC | Intellego to re-negotiate fees for Nhaka arguing for either a reduction in the management fees as an alternative to reducing the incentive fees. Or ask that the agreement captures that the fee will come down once the value reaches $100k. | Done | Farai
BOC | Submit a recommendation on TDB by end of week including determination of which of the two asset managers – OMIG and Imara – should subscribe for how much | Done | Farai
BOC | Propose exposure and funding for Greenfields debenture to enable Fund to make a formal commitment | Done | Farai
Haggie Rand | We were tasked with coming up with the best fixed income instruments of a short term with PA status that the Fund can invest its USD balances in. | Done | Farai
Simbisa | Recommendation on Tigere Greenfields | Done | Vongai
Innscor | To circulate a proposal for the offshore investment under zam- sanlam and TDB | Done | Vongai | Recommendation done and awaiting Review
Innscor | Put together a nhaka paper – analysis- track record- get insurance backed up facts if possible | Done | Vongai | ongoing- Report is being Finalised
Innscor | Recommendations- Fund to invest USD100K in nhaka, zam-sanlam USD100K, TDB – 11% of the Fund, 5% on Greenfields | Done | Vongai | Recommendation done and awaiting Review
Astra | Intellego to issue Origen and Greenfields debenture recommendations by Friday 22 Sept 2023 | Done | Tarie
Hippo | Come up with governance mechanisms for operator-property owner (PropCo-OpCo) relationships in the wake of challenges with Mbano and Baines Intercare | Done | Shandu
Hippo | Datvest to accrue and report on Mbano arrears and also charge interest so that we are all aware. As Intellego we may also need to track this. | Done | Shandu
Hippo | Nhaka site-visit to be arranged by administrator; | Done | Shandu
Minerva Copvol | Trustees proposing increased exposure to Origen. | Done | Shandu
NSSA | To work on the Greenfields debenture, and Eagle Reit Recommendations- Focusing on the Funding aspect | Done | Shandu
TMP | Tidy up reporting to show USD assets and ZWL assets separately | Done | Shandu
TMP | Recalculate the exposure to Delta as at 31 May 2023 after the recent movement in the interbank auction rate and advise the IC Chair for any action if over-exposure remains. | Done | Shandu
TMP | Do a comprehensive proposal on Nhaka including returns, attractions, fees, breeds, security, custodial arrangements, ownership transfer, etc for sign-off…differentiate option for member withdrawal from a biological asset investment. Need to educate members. Set minimum number of years served. Check with Nhaka if investing in non-pedigree will still qualify for PA. | Done | Shandu
TMP | Nhaka investment proposal to be finalized and presented at upcoming Trustees; | Done | Shandu
Engen | Minerva to send Intellego copy of CABSCUS SLA. We need to ensure we have copies of all signed SLAs for custodians | Done | Tapiwa
Engen | Correct the PA level after taking into account ZB compliance level | Done | Tapiwa
Engen | Resolution for investment into the TDB bond to be signed and OMIG to utilise USD36k in Nostro into TDB (to reach the 15% limit). OMIG already started process of deployment and expect to be done by July | Done | Tapiwa
Engen | Reports to show separate USD and ZWL | Done | Tapiwa
Engen | Do two sets of accounts – one for IPEC and another with hyperinflation accounting – to remove the audit qualification | Done | Tapiwa
Engen | Ensure physical split of assets including bank accounts. Asset managers provided the split but haven’t implemented as yet. | Done | Tapiwa
MCAZ | Administrator organising a breakfast meeting for Alternative investments-to officially invite stakeholders including Intellego | Done | Tapiwa
NBS | GREENFIELDS RECOMMENDATION | Done | Lazarus
Petrotrade | Report on sub-Acc 3 and ensure all asset managers (particularly ABCAM) separate their portfolios on a monthly basis | Done | Lazarus
Petrotrade | Check if the IPS requires to be reviewed | Done | Lazarus
Petrotrade | We had a matters arising on reviewing Asset Manager mandates and I just responded that these were done…kindly confirm? | Done | Lazarus
Astra | Financial review submitted to IPEC ,now waiting for response-Minerva | Done | Tarie
Astra | Next Trustees meeting scheduled for 30/11/2023-Minerva | Done | Tarie
Mimosa | Minerva to organise an induction for the new investment committee members and the new IPS workshop once it has been signed and approved | Done | Vongai
Mimosa | Minerva to arrange a tour of the properties around Harare for the new members in the committee | Done | Vongai
Cargo Carriers | •Zimnat Sanlam Wealth Fund Recommendation | Done | Farai
Cargo Carriers | •Agrowth Recommendation | Done
Cargo Carriers | •Update TDB investment numbers | Done
Goldridge | •TDB recommendation through Platinum | Done | Farai
MCAZ | •IPS Review | Done | Tapiwa
NOIC | •UDCORP housing scheme recommendation | Done | Tari
ABC | •Propose new asset manager mandates | Done
ABC | •Draft asset manager SLA's and propse a perfomance related fee structure for alternative investments | Done | Chris
BOC | •IPS Review | Done | Farai | Done
Debshan | •Sanlam Wealth Fund Recommendation | Done | Farai | Done
Debshan | •Greenfields Debenture Recommendation | Done
FBC | •TDB Recommendation | Done | Farai | Done
Mimosa | •VFSL Recommendation | Done | Tapiwa | Done
St Johns | •Include IPEC limits in IPS | Done
Zimsec | •Heka Bond Recommendation | Done
URL | •A paper on asset manager's perfomance and our recommendations | Done | Tari | Done
Hippo | •TDB recommendation | Done | Shandu/Tari | Done
TMP | •Greenfields Recommendation | Done | Shandu/Tari | Done
Nestle | •Greenfields Recommendation | Done | Lazie | Done
Nestle | •TDB Recommendation | Done |  | Done
Caaz | •Greenfields Recommendation | Done | Lazie | Done
Simbisa | •Sanlam Wealth Fund Recommendation | Done | Shandu | Done
Edgars | •An extended three year USD value trend analysis for the Fund to be shared. | Done | Tino | Done
Edgars | •Recommendations for USD assets in the market. | Done
Whitestone | • Prepare a proposal to give the Fund options on offshore investments | Done | Tino | Done
Falcon | •Sanlam Wealth Fund Recommendation | Done | Tino | Done
Brands Africa | •Tigere Recommendation | Done | Tari | Done
MCAZ | •UDCORP Property Analysis | Done | Tapiwa | Done
St Gobain | • TDB Recommendation | Done | Tapiwa | Done
Unilever | •TDB recommendation | Done | Shandu | Done
Unilever | •Agrowth Recommendation | Done
Unilever | •Origen Recommendation | Done
Falcon | •Sanlam Wealth Fund Recommendation | Done | Shandu/Tino | Done
NSSA | •Recommendation on the Sanlam Wealth Fund | Done | Shandu | Done
NSSA | •Recommendation on TDB | Done
Hippo Valley | •Sanlam Wealth Fund Recommendation | Done | Shandu/Tari | Done
TMP | •Recommendation on the Sanlam Wealth Fund | Done | Shandu/Tari
TIMB | •Recommendation on Sanlam Wealth Fund | Done | Tapiwa
Shamva | •TDB Recommendation | Done | Tari
Seedco | •Sanlam Wealth Fund Recommendation | Done | Tari
CAAZ | •Sanlam Wealth Fund Recommendation | Done | Lazie
TMP | •To include offshore strategy within the IPS (SAA) | Done | Shandu/Tari
Econet PF | •Sanlam Wealth Fund Recommendation | Done | Tari/Shandu
St Johns | •A paper on Funding options for 1 Shirley drive Property | Done | Tari/Shandu
Unilever | • Sanlam offshore Investment proposal and recommendation | Done
Unilever | • Greenfield (Tigere) Alternative Investment proposal and recommendation | Done | Tapiwa/Tari
Hippo | •IPS Completion | Done | Tari
NOIC | •IPS Completion and Tor | Done | Tari
FBC | Greenfields | Done | Lazie
FBC | •Sanlam Wealth Fund Recommendation | Done
Innscor | •Zimgold C/P | Done | Tari/Tapiwa
Innscor | •Zimnat Money Market | Done
Innscor | •Eagle Reit | Done
Innscor | •February Update | Done
Petrotrade | •TDB Recommendation | Done | Lazie
Petrotrade | •Request to advise on the maximum amount that the fund can put in a mortgage scheme | Done
Innscor | •Zimnat Money Market | Done | Tari/Tapiwa
The Joseph | •TDB and Sanlam Wealth recommendations | Done | Nyasha
RSC Steelforce | • Nhaka recommendation for the consortium | Done | Tino/Tapiwa
Barclays | Mangwana Rights Issue | Done | Tari
TIMB | • Intellego to issue a recommendation for Zimnat Financial services paper | Done | Tapiwa
Stanbic | •Sanlam Wealth Fund Recommendation | Done | Tapiwa
Stanbic | •Advise the client on how to thandlr proceeds from the Afreximbank shares in line with the custodial agreement | Done | Tapiwa
Minerva Funds | •One Pager on Troubled investments | Done | Tino
NSSA | •Eagle REIT Recommendation | Done | Tari
Mimosa | • List fixed income instruments under the fund's portfolio and their maturity dates | Done | Tari
CIPF | •IPS Review | Done | Tino
Barclays | Barclays House Proposals | Done | Tari
Barclays | Makasa Sun Funds Strategy | Done | Tari/Tapiwa
TMP | •Schedule of fees paid to asset managers | Done | Tatenda
Minerva Funds | •Recommendation on Invictus DRs | Done | Tino/Tapiwa
Minerva Funds | •Recommendation on Eagle REIT | Done
CIPF | •Eagle REIT Recommendation | Done | Tino
Dairiboard | •Analysis for the client to convert its current contract to a cattle backed investment. | Done | Tapiwa
Dairiboard | •Advisory Note on Centragrid Debt | Done | Tapiwa
Astra | •Origen Recommendation | Done | Lazie/Tari
Astra | •TDB recommendation | Done | Lazie/Tarie
ABC | • Comparison of current asset class exposures to IPEC limit | Done | Tapiwa/Tino
Petrotrade | •Mortgage Recommendation | Done | Lazie
Debshan | •Investment rationalizing plan in line with the revised investment guidelines for thr pension funds, including compliance with the minimum 20% | Done | Nyasha
Nssa | •Invictus Recommendation | Done | Tari
MCAZ | •Compliance Roadmap | Done | Tapiwa
St Johns | •Compliance Roadmap | Done | Tari/Nyasha
Brands Africa | •Update report | Done | Tari/Anesu
Minerva Funds | •Recommendation on Vakayi | Done | Tapiwa/Tino
St Johns | •Recommendation on which assets to liquidate | Done | Tari/Nyasha
Zimplow | •Compliance Roadmap | Done | Tari
Hippo | •Invictus Recommendation | Done | Tari
Stanbic | •Invictus Recommendation | Done | Tapiwa
TMP | •Appraisal for CT Bere on Fairview property | Done | Tatenda
Stanbic | •Invictus Recommendation | Done | Tapiwa
Nssa | •CAA recommendation | Done | Tari/Tapiwa
The Joseph | •Eagle REIT Recommendation | Done | Tari
TMP | •Asset Manager fees research Paper | Done | Tatenda
Hippo | •Eagle Recommendation | Done | Tari
Hippo | •Origen Recommendation | Done | Tari
Shangani Holistic | •Eagle Recommendation | Done | Nyasha
ABC | •Eagle Recommendation | Done | Tapiwa
Stanbic | •Eagle Recommendation | Done | Tapiwa
IDBZ | •Previous performances of the asset managers | Done | Tatenda
The Joseph | •Mangwana Rights Issue Recommendation | Done | Nyasha
Goldridge Schools | •Sanlam Wealth Fund Recommendation | Done | Nyasha
Astra | •Eagle REIT Recommendation | Done | Tatenda
Astra | •TDB Recommendation | Done | Tatenda
NOIC | •Kirkman Recommendation | Done | Tapiwa
PSMAS | •TDB Recommendation | Done | Nyasha
PSMAS | •Eagle Recommendation | Done | Nyasha
IDBZ | •ANALYSIS OF FUND HISTROICAL PERFORMANCE AND RECOMMENDATION OF ALLOCATION OF CONTRIBUTIONS | Done | Tatenda
EY | •Eagle REIT Recommendation | Done | Anesu/Tari
Masiye | •Recommendation on other asset managers that the Fund can consider | Done | Tino
The Joseph | •Request of a list of other member benefits outside of the pension scheme | Done | Nyasha
Shangani Holistics | •A paper on asset manager selection | Done | Nyasha/Tatenda
NOIC | • Mortgage Addition Recommendation | Done | Tari
NOIC | •TDB Recommendation | Done | Tari
Petrotrade | •Contribution Channeling Strategy | Done | Nyasha
ABC | •Sanlam Recommendation | Done | Tapiwa
Stanchart | •To prepare mandates for SCBZ P/F medical aid and Pensioners ex-gratia. | Done | Tatenda
Stanchart | •To prepare mandates for SCBZ P/F medical aid and Pensioners ex-gratia. | Done | Tatenda
Innscor | •Update asset manager Mandates | Done | Tari
AGS | TDB Recommendation | Done | Anesu
Innscor | •Review of current contribution allocation strategy among asset managers | Done | Tari
Sandvik | TDB,Agrowth and Eagle recommendations | Done | Tari
NBS | Eagle recommendation | Done | Tari
MCAZ | Recommendation on Pandora property disposal | Done | Tapiwa
NOIC | Recommendation on Brick and Mortar vote as well as Glenforest property investment | Done | Tari
TIMB | Eagle REIT Recommendation | Done | Tapiwa
The Joseph | Villa Monte Analysis | Done | Nyasha
NBS | TDB recommendation | Done | Nyasha
Freda Rebecca | Update Offshore Investments recommendation | Done | Tatenda
Shamva | •Assess whether the Assets transferring from MIPF are quality assets | Done | Welcome/Tatenda
IDBZ | •Recommend on how the Fund can dispose some of its properties and where the proceeds should be channelled to. | Done | Tatenda
TRB | Recommendations on tdb,sanlam,Agrowth and Eagle | Done | Tatenda
First Capital Bank | Recommend Disinvestment Proportion | Done | Tari
Mimosa | Portfolio Risk Analysis | Done | Tari
IDBZ | • Recommendation was done and went through review. | Done | Tatenda
NOIC | Draft done pending internal review by the team | Done | Tari
Dairiboard | Recommendation on how to generate liquidity for Mortgage | Done | Tapiwa
Girls Colledge | Offshore investments list | Done | Tino
Innscor | •Review of Trustees TOR | Done | Tari
Marsh | Portfolio US$ :zwg split | Done | Tapiwa
Econet | AGM report | Done | Tari
Stanbic | Review of the Borrowdale Brooke Property( In terms of Sale of Property) | Done | Tapiwa
PSMAS | Provide short-term investment instruments avaiable and associated costs | Done
Minerva Fund | Provide asset manager performance survey | Done | Tino /Tatenda
Minerva Fund | Fees recommendations regarding Alternative Investments | Done
MTC | Provide asset manager performance survey | Done | Tino /Tatenda
TMP | 3yr Asset Manager Perfomance Analysis | Done | Tari
TMP | Asset Manager Fees Monitoring | Done | Tari
TMP | To do a standard template for property investments for clarity. | Done | Tari
TMP | To separately assess the performance for Sub-account 3. | Done | Tari
TMP | To confirm with asset managers how they are handling failure risk due to investing in microfinance banks, especially small asset managers. | Done | Tari
Hippo | 3 yr Asset manager perfomance analysis | Done | Tari
Hippo | To correct errors on the fund performance results included in the pack and send the updated performance results to the trustees. | Done | Tari
Hippo | Analysis of Banks securitisation (Tier 1,2,3) | Done | Tari
ABC | Design Quarter Recommendation | Done | Tapiwa
Zimasco | Design Quarter Recommendation | Done | Tapiwa
Zimsec | To provide a recommendation paper on the smart suburb rights issue for consideration by the Board | Done | Tari
IPF | To reconcile Fund Values with asset manager values for Uniformity | Done | Tari
The Joseph | Nhaka fees recommendation | Done | Tari/Tapiwa
The Joseph | Platinum to complete the transaction for the purchase of Villa Montemarte flat for the Fund by Sept 30,2025 | Done | Tapiwa
Minerva Risk Advisors | Recommendation on which assets to liquidate to cover exiting member benefits | Done | Tino
NBS | Request to asses viable property investment opportunities under NBS that the Fund can invest in | Done | Tapiwa
IPF | To work on asset manager mandates and IPS to incorperate prior approval requirements for offshore investments | Done | Tari
Nestle | To facilitate new asset manager selection | Done | Tariro
St Johns | Recommendation on design quarter | Done | Tari
FBC PF | Intellego was requested to share a recommendation on the Villa Montmarte investment, including its impact on the overall portfolio | Done | Tatenda
TRB | Recommendation on TDB and Design Quarter | Done | Tatenda
Goldridge | To do an analysis of Asset Manager performance since inception and engage ZAM | Done | Tapiwa
Josephs PF | Intellego to release a recommendation for Zimcampus rights issue | Done | Tapiwa
Josephs PF | Intellego to send a schedule of Investments in the market | Done | Tapiwa
Hippo | To revisit the agreements to determine the asset manager fees are favorable to the fund. | Done | Tari/Tatenda
TMP | To come up with a report on fees to ensure fees charged by asset managers are standard. | Done | Tari/Tatenda
Cargo Carriers | 5 year perfomance of theFund | Done | Tatenda
TRB | Updated IPS | Done | Tatenda
Innscor | Recommendation on Sanlam | Done | Tari
Innscor | Recommendation on Eagle REIT | Done | Tari
CAAZ | Eagle REIT Recommendation | Done | Tari
Econet | Eagle REIT Recommendation | Done | Tari
Shamva | Perfomance Survey | Done | Tatenda
Falcon | To liase with CABS with regards to the differences on PA status values to understand the source of variance | Done | Tino/Tatenda
NSSA | Eagle Reit Conversion Analysis | Done | Tapiwa/Tari
St Johns | Eagle REIT Recommendation | Done | Tari
IPF | 2020-2024 Investment Summaries | Done | Tari
Nestle | Collective Invesments Schedule | Done | Tari
Simbisa Brands | September Update | Done | Tari
IPF | 5 year Perfomance | Done | Tari
Mimosa | Recommendation on which assets to trasfer from Sub Account B to Sub Account A post benefit payments | Done | Tari
Shamva | To provide a compliance on PA status | Done | Tatenda
Shamva | 3 year asset manager perfomance | Done
TRB | Provide an analysis on the viability of the the Nhaka investment | Done | Tatenda
TRB | Updated asset manager mandates | Done
Whitestone | To ask Nhaka on the possibilities of the Fund exiting before the 3 years and the possible implications to the Fund | Done | Tino
Whitestone | To do a paper on how the Fund should move forward since its now in paid up status | Done
Whitestone | To do a 5-year performance comparison of the 2 asset managers | Done
Sandvik | Sandvik requested recommendation for offshore which Zimnat proposed take lead. We will be doing follow-ups. | Done | Edwin
Sandvik | Provide performance analysis of the Victoria Falls Stock Exchange (VFEX), focusing on its relevance to the Fund's current or potential exposure and alignment with its long-term investment strategy. | Done | Edwin
Sandvik | Assess the potential impact of Zimbabwe's anticipated shift to a mono-currency regime on the Fund’s local and offshore investment positioning, offering insights on future opportunities and risks | Done | Edwin
Innscor Africa | Loan Payment TermSheet | Done
Simbisa | Recommendation on how to invest funds | Done
Simbisa | Our next report to include a detailed analysis on how the PAs are performing and Intellego is required to organise a strategy workshop on how SAA can be applied into strategy when conditions change | Done
FCB | IC Board Terms of reference | Done
Nestle | Feasibility of Mortgage Facility for Active Members | Done
Nestle | Girls College | Done
Nestle | Asset Manager Shortlist | Done | Done
Lafarge | Recommendation on how to invest funds | Done | Done
CAAZ | One pager on suitability of receiving Tbills as contribution arrears | Done | Tari
Minerva Funds | Paper on Alternative investments troubled assets | Done | Edwin | 20.3.2026
Innscor | Update on Member loan term sheet | Done | Tari | 16 .3.2026
Saint Gobain | Harava Solar Recommendation on Impairement | Done | Tapiwa | 26.3.2026
Innscor | Perfomance Analysis from January 2017 to September 2025 | Done | Tari | 24.3.2026
Mimosa | Liquidity Analysis | Done | Tari | 26.3.2026
FCB | Makasa Sun Strategy Review | Done | Tari | 26.3.2026
Simbisa | Datvest Liaison | Done | Tari | 25.3.2026
CIPF | Kavango Analysis | Done | Tatenda | 25.3.2026
FBC | Centrawest Recommendation | Done | Tatenda | 1.4.2026
Falcon | Kavango Analysis | Done | Edwin | 1.4.2026
NSSA | Kavango Analysis | Done | Tari | 1.4.2026
NOIC | Paper on the impact on the members and the Copany if they adopt the ZWG as the Mono Currency | Done | Tari | 7.4.2026
FCB | Centrawest Recommendation | Done | Edwin | 7.4.2026
IPF | ABCAM Termination Procedure | Done | Isaac | 10.4.2026
The Joseph | Update on Nhaka recommendation | Done | Tapiwa | 14.4.2026
The Joseph | Trevor Dollar Investment Analysis | Addressed | Tapiwa | 14.4.2026
IPF | VFEX portfolio and strategy assessment | Done | Tari | 15.4.2026
TIMB | Assessment of the NBS and POSB schemes to conduct an analysis of which to invest in | Done | Tapwa | 8.4.2026
Hippo | Mortgage Advisory Note | Done | Isaac/Tari | 17.4.2026
TMP | Mortgage Advisory Note | Done | Isaac/Tari | 17.4.2026
Econet | Mangwana Bridging Finance | Done | Isaac/Tari | 17.4.2026
Zimasco | Review and issue recommendations on the NBS mortgage proposal including funding method assuming adoption and comparison with alternative investment options | Done | Tapiwa | 23.4.2026
ABC | Eagle REIT Recommendation | Done | Tapiwa | 21.4.2026
The Joseph | Eagle REIT Recommendation | Done | Tapiwa | 19.4.2026
CAAZ | Update on the Contributions Arrears considering the actuarial valuation | Done | Tari | 21.4.2026
Note on C446: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It was communicated to the administrator that the investment was not investor ready. This is a land development project that is not yet saleable since allocation is still to be done, as such there is nothing to analyse for now